## How to use
RAID Log Template
by Rupesh Kumar · free to use and adapt
Type | R = Risk (might happen) · A = Assumption (believed true, needs validation) · I = Issue (has happened) · D = Dependency (needed from/by others)
Writing risks | Use cause → event → consequence. 'If X happens, then Y, because Z.'
Scoring | Probability and Impact on 1–5. Score = P × I. 15+ escalates to steering (red), 8–14 amber, below 8 green.
Dependencies | Always record Date needed and Date committed. The gap is your early warning.
Cadence | Review top-scored and overdue items weekly. Close items explicitly with a closure note.

## RAID Log
ID | Type | Title | Description (cause → event → consequence) | Workstream | Owner | Raised | Probability (1-5) | Impact (1-5) | Score | RAG | Mitigation / Action | Date needed | Date committed | Due / Review | Status | Closure note
R-001 | R | Hardware delivery slip | If the vendor misses the delivery date, wave 2 cutovers slip ≥3 weeks because change windows are booked 4 weeks ahead. | Network | PM | 2026-01-10 | 3 | 4 |  |  | Confirm dates in writing; identify alternative stock; pre-book backup windows. |  |  | 2026-01-24 | Open
A-001 | A | Out-of-hours site access | We assume site access is available out of hours for all wave 1 sites. | Facilities | Site lead | 2026-01-10 | 2 | 3 |  |  | Validate with each site manager by end of month. |  |  | 2026-01-31 | Open
D-001 | D | Firewall rule approval | Security team approval of new firewall rules required before cutover. | Security | Security lead | 2026-01-12 | 3 | 3 |  |  | Submit rules 3 weeks ahead; agree fast-track path. | 2026-02-05 | 2026-02-10 | 2026-02-01 | Open
I-001 | I | Test environment unavailable | Lab environment down; regression testing for wave 1 delayed by 2 days. | Network | Eng lead | 2026-01-15 | 5 | 2 |  |  | Use vendor lab as interim; escalate repair. |  |  | 2026-01-17 | Open